## Uttar Pradesh
M o n t h l y P r o g r e s s R e p o r t
Month and Year
Name of the State
Scheme
State | S.No. | Basieline Information for Project sanctioned by CSMC/CSC | [14 empty] | Fund Flow at SLNA |  |  |  | Number of Slums covered In Project | Project Implementation Information on Tenders / Packages |  |  | Schedule |  |  | Receipts from Beneficiaries, SLNA and Expenditure incuured & Utilisation | [6 empty] | Physical Progress in Project | [15 empty] | Remarks if any by
|  | Project Code allotted | City | Project Title | Project Cost | Central Share | Housing Cost | Infrastructure Cost | Sanction of DUs |  |  |  |  | Number of DUs catered in case of Project is having only infrastructure | Status and Date |  | Fund Received from State Government |  | Fund Released to implementing Agency |  |  | Estimated cost of all Packages in the Project and so cost of Awarded Packages and their estimated cost |  |  | Actual Start Date of First Package / tender | Schedule Completion of Last Package | Actual Completion Date if Project is completed by Constructing Agencies | Fund Received from SLNA / Beneficiaries / Interest Receipts |  |  | Expenditure incurred in Project |  | Balance Available with ULB in the Bank Account | Utilisation Certificate submitted to SLNA | Number of DUs for construction works taken up or under Progress | Completion of DUs |  |  |  |  | Number of DUs Allotted and Occupied | [6 empty] | Number of Non-Starter DUs due to various reason so far. | Infrastructure
[9 empty] | Construction of DUs - In-SItu | Construction of DUs under Relocation | DUs for Upgrade | Rental DUs | Transit DUs |  | Status -Sanction, Revised , Cancelled | Date | Central Share | Matching State Share | Central Share | Matching State Share |  | Sum of Sanction costs of components / items in all the awarded packages Tenders so far | Sum of Awarded Costs of packages / Tenders so far | Sanctioned cost of Components pending for Tendering |  |  |  | ACA received Received from SLNA | State Grant Received from SLNA | Funds collected from Beneficiary | Paid to Project constructing Agencies/ contractors | Fund released to Beneficiaries in case of Beneficiaries led Construction |  |  |  | New Construction in -Situ | New Construction Under Relocation | Rental DUs | Transit DUs | Upgrade | Allotment to SCs | Allotment to STs | Allotment to Minorities | Allotment to OBCs | Allotment to Others | Total DUs Allotted So Far | Total Occupied DUs in all categories |  | Value of work undertaken/ commenced | Value of work Completed so far | SLNA/Implementing Agency (ULB)
[5 empty] | Rs. In Lakh |  |  |  | Nos |  |  |  |  | Nos | Status | Date | Rs. In Lakh |  |  |  | Nos | Rs. | Rs. | Rs. | Date | Date | Date | Rs. In Lakh | [6 empty] | Nos | Nos |  |  |  |  | Nos |  |  |  |  | Nos. |  | Nos | Rs. | Rs.
| 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31 | 32 | 33 | 34 | 35 | 36 | 37 | 38 | 39 | 40 | 41 | 42 | 43 | 44 | 45 | 46 | 47 | 48 | 49 | 50
| H1 | H2 | H3 | H4 | H5 | H6 | H7 | H8 | H9 | H10 | H11 | H12 | H13 | H14 | H15 | H16 | S1 | S2 | S3 | S4 | U1 | U2 | U3 | U4 | U5 | U6 | UG A | U7 | U8 | U8 | U9 | U10 | U11 | U12 | U13 | U14 | U15 | U16 | U17 | U18 | U19 | U20 | U21 | U22 | U23 | U24 | U25 | U26 | U27 | U28
Uttar Pradesh |  |  | Agra | Pilot DPR under RAY for identified slums as per SFCP, Agra | 37.6959 | 14.3936 | 14.675 | 23.0209 | 305 | [6 empty] | 2013-01-11 | 4.7979
Uttar Pradesh |  |  | Lucknow | Pilot DPR under RAY for in-situ development of 5 slums namely Gaur Bheet, Bharat Nagar, chamrahi, Shivlokpur, Daud Nagar & Naya daud nagar in Faizullahganjward Lucknow | 24.7535 | 10.7521 | 14.2819 | 10.4716 | 468 | [6 empty] | 2013-01-11 | 3.584
Uttar Pradesh |  |  | Rampur | Pilot DPR for Magjeen Mohalla at Rampur under RAY. | 13.6718 | 5.1963 | 3.0912 | 10.5806 | 96 | [6 empty] | 2012-12-05 | 1.7321
Uttar Pradesh |  |  | Rae Bareli-Phase I | Pilot DPR for identified 4 slums ( 1. Munshiganj, 2. Mohiddinpur, 3. Shah Tola and 4. Ghosiyana under RAY, Rae Bareli (Phase-I). | 64.6076 | 29.6707 | 17.2647 | 47.3429 | 638 | [6 empty] | 2012-12-05 | 9.8902
Uttar Pradesh |  |  | Rae Bareli-Phase II | Pilot DPR for identified slums as per SFCP under RAY Rae Bareli (Phase-II). | 52.9101 | 23.3737 | 26.2823 | 26.6278 | 785 | [6 empty] | 2013-01-11 | 7.7912
Uttar Pradesh |  |  | Kanpur | Pilot DPR for Harbansh Mohal Slum Improvement project under RAY | 5.1831 | 2.0705 | 2.4001 | 2.783 | 48 | [6 empty] | 2012-12-21 | 0
Uttar Pradesh |  |  | Kanpur | Pilot DPR for Pokhar Purva Slum Improvement project under RAY | 8.2476 | 3.0134 | 3.4695 | 4.7781 | 80 | [6 empty] | 2012-12-21 | 0
Uttar Pradesh |  |  | Kannouj | Pilot DPR for in-site Upgradation of Shekhana & Bajariya Shekhana slums in Kannauj under RAY | 17.5257 | 6.5749 | 7.6145 | 9.9112 | 164 | [6 empty] | 2012-12-21 | 0
[5 empty] | 224.5953 | 95.0452 | 89.0792 | 135.5161 | 2584 | [7 empty] | 27.7954